## Sheet1
Risk Analysis |  |  |  |  | Risk Strategies
Risk | Probability | Effects |  |  | Risk | Strategy | Task | Effort (person-days) | Duration (days) | Dependencies
Server computer cannot be able to use in class. | High | Serious |  |  | Network problem | We would like to use mobile hotspot instead of campus internet. | Planning - T1 | 7 | 7 |  | Barış
The IP address may not be accessed stably on the campus's Internet. | High | Serious |  |  | Staff illness | Reorganize team so that there is more overlap of work and people therefore understand each other’s jobs. | Requirement Analysis - T2 |  | 7 | T1 | Efe
The size of the software is underestimated. | Moderate | Tolerable |  |  | Defective components | We need exact 3 computers. If something happens to computers, we will substitute the computers. | Design - T3 |  | 14 | T2 | Emir
Database integration failure. | Low | Serious |  |  | Database problem | In case of not integrating datas to the database, we will use CSV to save the datas. | Implementation - T4 |  | 7 | T3 | Emre
Possible delay between player-controller. | Moderate | Serious |  |  |  |  | Software Design Document (SDD) - T5 |  | 14 | T4 | Etkin
Programming languages can't communicate with each other. | Moderate | Serious |  |  |  |  | SDD version-2 - T6 |  | 7 | T5 | Metin
Programming languages can't communicate with each other. | Moderate | Serious |  |  |  |  | Database Management - T7 |  | 7 | T6
Programming languages can't communicate with each other. | Moderate | Serious |  |  |  |  | Game Coding - T8 |  | 3 | T6
Programming languages can't communicate with each other. | Moderate | Serious |  |  |  |  | Sensor Coding - T9 |  | 3 | T6
Programming languages can't communicate with each other. | Moderate | Serious |  |  |  |  | Testing - T10 |  | 7 | T9,T8,T7
Programming languages can't communicate with each other. | Moderate | Serious |  |  |  |  | STR + SAR + Demo - T10 |  |  | T10
Programming languages can't communicate with each other. | Moderate | Serious
Programming languages can't communicate with each other. | Moderate | Serious
Programming languages can't communicate with each other. | Moderate | Serious
Name | Strategy | Strategy | Strategy | Strategy | Strategy
Network problem | We would like to use mobile hotspot instead of campus internet.
Staff illness | Reorganize team so that there is more overlap of work and people therefore understand each other’s jobs.
Defective components | We need exact 3 computers. If something happens to computers, we will substitute the computers.
Database problem | In case of not integrating datas to the database, we will use CSV to save the datas.

## Sheet2
Name | Brand | CPU | GPU | OS | Storage | Memory
Barış Tüdeş
Efe Soykan
Emir Ulurak
Emre Beşik
Etkin Kınık
Metin Karaca | Macbook Pro 14' 2021 | M1 Pro | M1 Pro GPU | MacOS Monterey Version 12.6 | 512GB SSD | 16GB RAM LPDDR5