## Sheet1
Risk Analysis |  |  | Risk Strategies
Risk | Probability | Effects | Risk | Strategy | Task | Effort (person-days) | Duration (days) | Dependencies
Server computer can't useful in class. | High | Serious |  |  | Software Development Plan (SDP) - T1 | 7 | 7 |  | Barış
The IP address may not be accessed stably on the school's Internet | High | Serious |  |  | SDP version-2 - T2 |  | 7 | T1 | Efe
The size of the software is underestimated. | Moderate | Tolerable |  |  | SRS + STP - T3 |  | 14 | T2 | Emir
[5 empty] | SRS version-2 and STP version-2 - T4 |  | 7 | T3 | Emre
[5 empty] | Software Design Document (SDD) - T5 |  | 14 | T4 | Etkin
[5 empty] | SDD version-2 - T6 |  | 7 | T5 | Metin
[5 empty] | Database Management - T7 |  | 7 | T6
[5 empty] | Game Coding - T8 |  | 3 | T6
[5 empty] | Sensor Coding - T9 |  | 3 | T6
[5 empty] | Testing - T10 |  | 7 | T9,T8,T7